HKUPOP Student Research Project

Yau Tsim Mong District Council Jordan East Constituency

By-election of 5 October 2008

Outline of Project Activities and Assignments (draft as on 29 September 2008)

General Design

There will be 4 project groups, each comprising about equal number of university and secondary students. Each group shall elect one group leader to liaise with HKUPOP via Project Coordinator Mr Frank Lee at frank.lee@hkupop.hku.hk.

The project shall comprise of 4 different modules –

- A library study of the constituency

- An onsite study within the constituency BEFORE the election

- An onsite study within the constituency on the election day

- A write-up report incorporating (1), (2), (3) and POP's exit poll findings

Pre-election Written Assignments

Each group shall collectively produce one document each for everybody’s reference before Friday 3 October 2008 –

- Description of the profile of the constituency and its electorate.

- Description of the election record of the constituency or area since 1982 (for all tiers of elections).

- Documentation of all media stories of the by-election.

- Compilation of candidate profiles for the by-election.

Pre-election Observation and Assignments

Each group shall take turn to visit the constituency according to the following time table, and each member of each group shall write and submit one written report to HKUPOP via Mr Frank Lee at frank.lee@hkupop.hku.hk using the standard Fieldwork Report Forms -

- Onsite street observation of all campaign activities on 1 October 2008, Wednesday, plus some casual interviews with candidates, campaign workers, ordinary citizens.

- Onsite street observation of all campaign activities on 2 October 2008, Thursday, plus some casual interviews with candidates, campaign workers, ordinary citizens.

- Onsite street observation of all campaign activities on 3 October 2008, Friday, plus some casual interviews with candidates, campaign workers, ordinary citizens.

- Onsite street observation of all campaign activities on 4 October 2008, Saturday, plus some casual interviews with candidates, campaign workers, ordinary citizens.

Election Day Observation and Assignments

Each group shall take turn to visit the constituency according to the following time table, and each member of each group shall write and submit one written report to HKUPOP via Mr Frank Lee at frank.lee@hkupop.hku.hk using the standard Fieldwork Report Forms -

- Onsite observation of campaign activities and voting behaviour on election day, from 0700-1100 hrs.

- Onsite observation of campaign activities and voting behaviour on election day, from 1100-1500 hrs.

- Onsite observation of campaign activities and voting behaviour on election day, from 1500-1900 hrs.

- Onsite observation of campaign activities and voting behaviour on election day, from 1900-2300 hrs.

Post-election Assignments

All groups shall pool all observations and library study results together, plus POP's exit poll findings, and then write papers or reports on different themes, topics to be discussed, submission deadline to be confirmed.

University students can suggest topics which are relevant to their coursework assignments, while secondary students can write any articles, reports, powerpoints, etc. according to their own interest. All papers such output by university and secondary students would be collated into HKUPOP’s final project report.